## Task Management
Task ID | Project ID | Task Name | Start Date | End Date | Assigned To | Progress (%) | Issues
T001 | P001 | Surface Preparation | 2025-01-02 | 2025-01-05 | Manager A | 50 | None
T002 | P001 | Primer Application | 2025-01-10 | 2025-01-15 | Manager B | 30 | Delay in material
T003 | P001 | Final Coating | 2025-02-16 | 2025-02-20 | Manager A | 0 | Pending Approval
T004 | P001 | Inspection | 2025-03-01 | 2025-03-05 | Manager C | 0 | Not Started
T005 | P001 | Quality Check | 2025-03-02 | 2025-03-06 | Manager C | 0 | Not Started
T006 | P001 | Curing Process | 2025-03-03 | 2025-03-07 | Manager A | 0 | Pending Review
T007 | P001 | Final Touch-Up | 2025-03-04 | 2025-03-08 | Manager B | 0 | Not Assigned
T008 | P001 | Packaging | 2025-03-05 | 2025-03-09 | Manager C | 0 | Awaiting Materials
T009 | P001 | Dispatch Preparation | 2025-03-06 | 2025-03-10 | Manager A | 0 | Not Started
T010 | P001 | Final Inspection | 2025-03-07 | 2025-03-11 | Manager B | 0 | Pending Confirmation

## Resource Allocation
Employee ID | Employee Name | Role | Project ID | Task Assigned | Hours Allocated
E001 | Alice | Supervisor | P001 | Surface Preparation | 20
E002 | Bob | Technician | P001 | Primer Application | 30
E003 | Charlie | Painter | P001 | Final Coating | 25
E004 | David | Inspector | P001 | Inspection | 15
E005 | Emma | Quality Analyst | P001 | Quality Check | 18
E006 | Frank | Technician | P001 | Curing Process | 22
E007 | Grace | Painter | P001 | Final Touch-Up | 20
E008 | Henry | Supervisor | P001 | Packaging | 25
E009 | Ivy | Logistics | P001 | Dispatch Preparation | 15
E010 | Jack | Coordinator | P001 | Final Inspection | 10

## Material Tracking
Material ID | Material Name | Project ID | Quantity Required | Quantity Used | Supplier | Status
M001 | Primer | P001 | 50 | 25 | Supplier A | In Stock
M002 | Coating Paint | P001 | 100 | 40 | Supplier B | Partial Usage
M003 | Sealer | P001 | 75 | 0 | Supplier C | Not Delivered
M004 | Sandpaper | P001 | 30 | 20 | Supplier D | In Stock
M005 | Thinner | P001 | 60 | 30 | Supplier E | Partial Usage
M006 | Protective Tape | P001 | 40 | 15 | Supplier F | In Stock
M007 | Adhesive | P001 | 50 | 10 | Supplier G | In Stock
M008 | Brushes | P001 | 100 | 50 | Supplier H | In Stock
M009 | Cleaning Solvent | P001 | 80 | 35 | Supplier I | Partial Usage
M010 | Packing Material | P001 | 90 | 60 | Supplier J | In Stock

## Costing & Budgeting
Task ID | Project ID | Estimated Cost | Actual Cost | Material Cost | Labor Cost | Status
T001 | P001 | 500000 | 250000 | 100000 | 150000 | On Budget
T002 | P001 | 750000 | 0 | 0 | 0 | Pending Start
T003 | P001 | 600000 | 300000 | 120000 | 180000 | On Budget
T004 | P001 | 850000 | 600000 | 250000 | 350000 | Under Budget
T005 | P001 | 700000 | 750000 | 280000 | 470000 | Over Budget
T006 | P001 | 900000 | 400000 | 200000 | 200000 | On Budget
T007 | P001 | 650000 | 500000 | 180000 | 320000 | On Budget
T008 | P001 | 720000 | 0 | 0 | 0 | Pending Start
T009 | P001 | 880000 | 780000 | 300000 | 480000 | Under Budget
T010 | P001 | 930000 | 950000 | 400000 | 550000 | Over Budget

## Progress Tracking
Task ID | Project ID | Milestones Completed | Open Issues | Delays (Days) | Risk Level | Overall Status
T001 | P001 | 2 | 1 | 5 | Medium | On Track
T002 | P001 | 0 | 1 | 0 | Low | Pending Start
T003 | P001 | 3 | 2 | 4 | High | At Risk
T004 | P001 | 1 | 0 | 3 | Medium | On Track
T005 | P001 | 4 | 3 | 6 | High | Delayed
T006 | P001 | 2 | 1 | 4 | Medium | On Track
T007 | P001 | 3 | 2 | 2 | High | At Risk
T008 | P001 | 1 | 0 | 3 | Medium | On Track
T009 | P001 | 2 | 1 | 5 | Medium | On Track
T010 | P001 | 4 | 3 | 6 | High | Delayed

## Dashboard
Task ID | Completion (%) | Open Issues | Budget Status | Overall Status
T001 | 50 | 1 | On Budget | On Track
T002 | 30 | 1 | Pending Start | Pending Start
T003 | 0 | 2 | On Budget | At Risk
T004 | 0 | 0 | Under Budget | On Track
T005 | 0 | 3 | Over Budget | Delayed
T006 | 0 | 1 | On Budget | On Track
T007 | 0 | 2 | On Budget | At Risk
T008 | 0 | 0 | Pending Start | On Track
T009 | 0 | 1 | Under Budget | On Track
T010 | 0 | 3 | Over Budget | Delayed