## Project_Management_Tracker
Task ID | Project ID | Task Name | Start Date | End Date | Assigned To | Progress (%) | Issues
T001 | P002 | Site Preparation | 2025-01-02 | 2025-01-05 | Manager X | 60 | None
T002 | P002 | Foundation Setup | 2025-01-10 | 2025-01-15 | Manager Y | 40 | Material Shortage
T003 | P002 | Structural Work | 2025-02-16 | 2025-02-20 | Manager Z | 20 | Weather Delays
T004 | P002 | Electrical Setup | 2025-03-01 | 2025-03-05 | Manager X | 10 | Inspection Pending
T005 | P002 | Plumbing Work | 2025-03-02 | 2025-03-06 | Manager Y | 5 | Technician Unassigned
T006 | P002 | Roofing Completion | 2025-03-03 | 2025-03-07 | Manager Z | 0 | Not Started
T007 | P002 | Painting | 2025-03-04 | 2025-03-08 | Manager X | 0 | Pending Approval
T008 | P002 | Interior Finishing | 2025-03-05 | 2025-03-09 | Manager Y | 0 | Awaiting Materials
T009 | P002 | Final Inspection | 2025-03-06 | 2025-03-10 | Manager Z | 0 | Not Started
T010 | P002 | Handover | 2025-03-07 | 2025-03-11 | Manager X | 0 | Pending Confirmation

## Project_Employee_Assignment
Employee ID | Employee Name | Role | Project ID | Task Assigned | Hours Allocated
E011 | Liam | Supervisor | P002 | Site Planning | 35
E012 | Olivia | Technician | P002 | Electrical Setup | 28
E013 | Noah | Painter | P002 | Wall Painting | 40
E014 | Sophia | Inspector | P002 | Safety Inspection | 20
E015 | Mason | Quality Analyst | P002 | Quality Assurance | 22
E016 | Ava | Technician | P002 | Wiring Setup | 32
E017 | Ethan | Painter | P002 | Final Touch-Up | 30
E018 | Isabella | Supervisor | P002 | Project Management | 38
E019 | Jacob | Logistics | P002 | Materials Transport | 18
E020 | Amelia | Coordinator | P002 | Final Review | 12

## Material_Inventory_Updated
Material ID | Material Name | Project ID | Quantity Required | Quantity Used | Supplier | Status
M011 | Cement | P002 | 200 | 100 | Supplier K | In Stock
M012 | Concrete Mix | P002 | 150 | 80 | Supplier L | Partial Usage
M013 | Steel Bars | P002 | 120 | 50 | Supplier M | In Stock
M014 | Wooden Planks | P002 | 180 | 120 | Supplier N | In Stock
M015 | Nails | P002 | 300 | 150 | Supplier O | Partial Usage
M016 | Glass Panels | P002 | 90 | 30 | Supplier P | Not Delivered
M017 | Paint Brushes | P002 | 60 | 45 | Supplier Q | In Stock
M018 | Safety Gear | P002 | 50 | 25 | Supplier R | In Stock
M019 | Adhesive Tape | P002 | 100 | 70 | Supplier S | Partial Usage
M020 | Construction Gloves | P002 | 80 | 50 | Supplier T | In Stock

## Project_Cost_Tracking
Task ID | Project ID | Estimated Cost | Actual Cost | Material Cost | Labor Cost | Status
T011 | P002 | 600000 | 300000 | 120000 | 180000 | On Budget
T012 | P002 | 800000 | 0 | 0 | 0 | Pending Start
T013 | P002 | 700000 | 350000 | 150000 | 200000 | On Budget
T014 | P002 | 950000 | 800000 | 350000 | 450000 | Under Budget
T015 | P002 | 500000 | 550000 | 200000 | 350000 | Over Budget
T016 | P002 | 850000 | 400000 | 180000 | 220000 | On Budget
T017 | P002 | 750000 | 650000 | 250000 | 400000 | On Budget
T018 | P002 | 900000 | 0 | 0 | 0 | Pending Start
T019 | P002 | 950000 | 900000 | 370000 | 530000 | Under Budget
T020 | P002 | 1000000 | 1100000 | 450000 | 650000 | Over Budget

## Project_Task_Tracking
Task ID | Project ID | Milestones Completed | Open Issues | Delays (Days) | Risk Level | Overall Status
T011 | P002 | 3 | 2 | 4 | High | At Risk
T012 | P002 | 1 | 1 | 2 | Medium | On Track
T013 | P002 | 4 | 0 | 0 | Low | On Track
T014 | P002 | 2 | 3 | 5 | High | Delayed
T015 | P002 | 3 | 1 | 3 | Medium | On Track
T016 | P002 | 5 | 0 | 1 | Low | On Track
T017 | P002 | 4 | 2 | 6 | High | Delayed
T018 | P002 | 2 | 1 | 2 | Medium | On Track
T019 | P002 | 3 | 0 | 3 | Low | On Track
T020 | P002 | 1 | 4 | 7 | High | At Risk

## Dashboard_Task
Task ID | Progress (%) | Issues Open | Budget Status | Overall Status
T011 | 60 | 1 | On Budget | On Track
T012 | 40 | 2 | Pending Start | Pending Start
T013 | 0 | 3 | On Budget | At Risk
T014 | 80 | 0 | Under Budget | On Track
T015 | 20 | 4 | Over Budget | Delayed
T016 | 90 | 1 | On Budget | On Track
T017 | 50 | 2 | On Budget | At Risk
T018 | 70 | 0 | Pending Start | On Track
T019 | 30 | 1 | Under Budget | On Track
T020 | 10 | 3 | Over Budget | Delayed